## 2014 MS4 Permit Tasks
Appendix A. TMDL Activity and BMP Summary
The table below lists stormwater BMPs that are targeted to improve water quality impairments listed by TMDL affected, and the SWMP section they apply to. If the BMP addresses a TMDL, high (H), medium (M) or low (L) priority is indicated, or G indicates general implementation. Progress through August 2021 is summarized for each BMP
[Insert MS4 Name]
Section* | SWMP Actions for (insert municipality name here) | Phosphorus TMDL | Biota (Flow, sedimentation) TMDL | E.coli TMDL | Progress Summary
ERP | Track instances of non-compliance as required under the permit | G | G | G | Ongoing. See report summary.
PPP | Access to the stormwater management plan | G | G | G | Provided.
PPP | Stormwater Advisory Group (Watershed group), and | G | G | G | Meetings 3-4 times per year
PPP | Stormwater Management Program (SWMP) review. | G | G | G | Completed. At least annual review.
PPP | Participation in Watershed Groups | G | G | G | Participate in Middle Huron Partners, facilitated by HRWC.
PEP | Distribute Informational Materials | H | H | H | Multiple materials distributed. See PEP report
PEP | Watershed Community Calendar | G | G | G | Annual distribution. See PEP report.
PEP | Information in Community Newsletters and on Websites - Educational Content | G | G | G | Regular inclusion. See PEP report.
PEP | Local Newspaper and Web/Other Advertisements | G | G | G | Multiple web and media ads. See PEP report.
PEP | Promote Water Resource Protection Workshops | H | H | H | Multiple workshops promoted. In-person workshops were cancelled or rescheduled in 2020-21 due to Covid-19. See PEP report.
PEP | Volunteer Stream Monitoring | G | G | G | Promote volunteer participation. See PEP report. HRWC coordinates monitoring. See Section 9 report.
PEP | Catchbasin/Storm Drain Labeling | H | M | H | Continuing to identify and label by subwatershed. See PEP report.
PEP | Riparian Land Management Information | H | H | H | Continued with distribution of materials. See PEP report.
PEP | Displays and Outreach at Local and Regional Fairs and Community Events | G | G | G | Participated in multiple events. Many events were cancelled or rescheduled in 2020-21 due to Covid-19. See PEP report.
PEP | Promote County-wide Compliant Tracking and Response System | G | G | G | Coordinated with county. See PEP report.
PEP | Stream and River Crossing Road Signs | G | G | G | Completed.
PEP | Washtenaw County Community Partners for Clean Streams | G | G | G | Continued to implement. See PEP report.
PEP | Washtenaw County Pollution Prevention Inspections | H | L | H | Continued to implement. See PEP report.
PEP | Washtenaw County Issues of the Environment Radio Show | G | G | G | Continued to implement. See PEP report.
PEP | Washtenaw County Environmental Excellence Awards | G | G | G | Continued to implement. See PEP report.
PEP | Washtenaw County Fats, Oil and Grease & Litter Reduction | G | G | G | Continued to implement. See PEP report.
PEP | Washtenaw County River Safe Homes Program | G | G | G | Continued to implement. See PEP report.
PEP | Washtenaw County & City of Ann Arbor Residential Rain Garden Program | H | H | M | Continued to implement. See PEP report.
PEP | Washtenaw County Home Toxics Reduction Program | G | G | G | Continued to implement. See PEP report.
PEP | Washtenaw County Drug Take Back Program | G | G | G | Continued to implement. See PEP report.
IDEP | Dry Weather Screening Program & Data Collection | M | L | H | Continued to implement. Some screening was delayed by Covd-19. See IDEP report.
IDEP | Illegal Dumping/Spill Response & Database | G | G | G | Continued to implement. See IDEP report.
IDEP | Environmental reporting line / Tracking | G | G | G | Continued to implement. See IDEP report.
IDEP | Time of Sale & Field Inspections | M |  | H | Continued to implement county progrm. See IDEP report.
IDEP | Pollution Prevention (P2) Program | M | L | H | Continued to implement. See IDEP and P2 reports.
IDEP | Staff Training | M | L | H | Staff received new training and refresher training. Some training was cancelled or rescheduled due to Covid-19. See IDEP report.
IDEP | Dye Testing | M | L | H | Dye testing was carried out where appropriate. Some dye testing was delayed due to Covid-19. See IDEP report.
SESC | Soil Erosion and Sedimentation Control (SESC) Programs | H | H |  | Continued to implement. See SESC report.
SESC | SESC Inspections | H | H |  | Continued to implement. See SESC report.
SESC | Discharge notifications | H | H |  | Continued to implement. See SESC report.
SESC | State of Michigan – Permit-by-Rule Notification | H | H |  | Completed.
PCSW | Require PCSW controls within jurisdiction, including on WC projects | G | G | G | Completed. Ongoing.
P2GH | Municipal Facility & Structural Stormwater Control Inventory | G | G | G | Completed.
P2GH | Regulated Municipal Facility – Assessment of Potential for Pollutant Discharge | G | G | G | Completed.
P2GH | Catch basin cleaning | H | H | M | Ongoing. See report summary.
P2GH | Lot sweeping | H | M | L | Ongoing. See report summary.
P2GH | Litter collection | G | G | G | Ongoing. See report summary.
P2GH | Proper Handling & Disposal of Operation and Maintenance Waste | H | M | L | Ongoing. See report summary.
P2GH | Employee/Contractor Training | G | G | G | Staff received new training and refresher training. Some training was cancelled or rescheduled due to Covid-19. See summary report.
P2GH | Staff Certifications | G | G | G | Staff received certification following training.
P2GH | IDEP Training | G | G | G | Staff received new training and refresher training. Some training was cancelled or rescheduled due to Covid-19. See summary report.
P2GH | Management of County-owned Vegetated Properties | H | M |  | Ongoing. See report summary.
ADDL | Swift Run Rain Gardens | H | H | M | Installed by HRWC for Swift Run TMDL.
ADDL | Ford Lake dam management | H |  |  | Continued by Ypsilanti Township.
ADDL | Honey Creek Implementation Project | M | M | H | Multiple BMPs completed by HRWC and Scio Township.
ADDL | Whole Farms for Clean Water | H | M | M | Ongoing HRWC program to implement agricultural BMPs to reduce phosphorus loss.
ADDL | [add additional municipal projects or remove rows]
* Key:
ERP | Enforcement Response Procedure
PPP | Public Participation Plan
PEP | Public Education Plan
IDEP | Illicit Discharge and Elimination Plan
SESC | Construction Soil Erosion and Sediment Control
PCSW | Post-Construction Stormwater Runoff Program
P2GH | Pollution Prevention and Good Housekeeping
ADDL | Additional projects or BMPs